| TRIANGLE INDUSTRIAL CITY IMPROVEMENT DISTRICT NPC (CID/SRA) ANNUAL IMPLEMENTATION PLAN 1st July 2017 to 30th June 2018 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PROGRAM 1 – MANAGEMENT & OPERATIONS |  |  |  |  |  |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Effective Management of the SRA by a Board of Directors elected by its Members and operated by a management team that is appointed by the Board of Directors. | Directors Manager | Ongoing | 1st July 2017 – 30th June 2018 | Quarterly feedback at Board meetings. | Effective Management will be aimed at facilitating investment in the area with promotion of economic growth and sustainable development coupled with new job creation activities. These would relate to environmental issues, effective communication with property / business owners, and promotion of membership to the SRA, etc. |
| -Operational SRA office. | Directors Manager | Ongoing | 1st July 2017 – 30th June 2018 | Appointment of staff and provision of functional SRA office open to all property owners. |  |
| -Board Meetings. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Quarterly Board meetings with reports tabled by different portfolio chairs. |  |
| -Financial report to COCT. | Director - Finance | Ongoing | 1st July 2017 – 30th June 2018 | Submit reports timeously by the 15th of the following month. |  |
| -Audited Financial Statements. | Finance Director | Annually | 1st July 2017 – 30th June 2018 | Unqualified Financial Audits submitted by 31 August to COCT. |  |
| -Communicating arrears list. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Table at Board meeting – observe and report concern over outstanding amount. |  |
| -AGM. | Manager | Annually | 1st July 2017 – 30th June 2018 | Host AGM and provide members with relevant information. |  |
| 2. Effective Management of Finances. | SRA Board of Directors, Book keeper and Auditors. Director – Finance. | Ongoing | 1st July 2017 – 30th June 2018 | Preparation of budgets, regulation of expenditure, careful consideration of capital expenditure, regular inspection of financial status and financial registers. | The SRA Board of Directors has numerous control mechanisms in place pertaining to approval of expenditure and record keeping. |
| -Mid-year review | Manager | Annually | 1st July 2017 – 30th June 2018 | Submit to COCT by end of January. |  |
| 3. Promote Membership to the SRA, encouraging active participation in decision making processes. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Use of Newsletters, visit to companies, Annual General Meetings. Report to SRA Board. |  |
| 4. Facilitate effective communication with business owners and SRA Members thus enabling the SRA to provide an efficient service. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Newsletters, meetings, reports to SRA Board. |  |
| 5. Continued updating of SRA Data Base in order to promote effective communication with property/ business owners on their integration into the SRA area. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Visits to newcomers. Promotion of SRA’s activities in newsletter. |  |
| -Submit Management Report and Annual Financial Statements to Sub-Council. | Manager | Annually | 1st July 2017 – 30 June 2018 | Within 3 months of AGM. |  |
| -Manage and monitor C3 notification process. | Manager | Monthly | 1st July 2017 – 30 June 2018 | Report number of C3 notification per month to Board. |  |
| -Submit input to COCT IDP (Integrated Development Plan) | Manager | Annually | 1st July 2017 – 30 June 2018 | Annual submission to Sub Council. |  |
| -Submit input to COCT Capital Budget. | Manager | Annually | 1st July 2017 – 30 June 2018 | Annual submission to Sub Council. |  |
| -Review SRA Budget. | Director - Finance | Annually | 1st July 2017 – 30 June 2018 | Submit review budget to COCT by 31 January. |  |

| PROGRAM 2 – SECURITY / LAW ENFORCEMENT INITIATIVES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Review of current public safety plan. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Incorporate in Public Safety Plan. |  |
| 2. Keep record of crime statistics/ incidents and identify “hot spot” areas. | Manager Security Service Provider | Monthly | 1st July 2017 – 30th June 2018 | Measurement. Comparisons. Monthly submission to Board. |  |
| 3. Identify the root causes of crime by conducting the necessary research/ analysis. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Quarterly evaluation of the number/type of root causes identified and amend operational plan. |  |
| 4. Identify environmental design contributing to crime. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Quarterly evaluation of environmental design contributing to crime and amend operational plan. |  |
| 5. Address root causes of crime in conjunction with the SAPS, Local Authority, Security Service and other stake holders. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Number of contributing factors addressed through stakeholders reported to Board monthly . |  |
| 6. Liaise with the South African Police Service with regard to the effective policing of the SRA area. | Manager | Monthly | 1st July 2017 – 30th June 2018 | Monthly meetings with the relevant role players within SAPS and give feedback to service provider and Board. |  |
| 7. Identify shortcomings of the SAPS in relation to the effective policing of the SRA area. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Quarterly evaluation of shortcomings and amend operational plan accordingly. |  |
| 8. Co-operate with the SA Police Service. Active participation by SRA and assistance to Police by gathering relevant information to facilitate the development and implementation of both effective and practical crime prevention strategies for the SRA area. | Manager | Monthly | 1st July 2017 – 30th June 2018 | Monthly meetings with the SA Police Service with monthly report to the SRA Board. |  |
| 9. On-site inspection of security patrol officer. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Report findings to Board with recommendations where applicable. |  |
| 10. Provide an efficient Public Safety Service. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Appointment of Public Safety service provider by means of a competitive process (2 year contract) and deployment of officers accordingly. |  |
| 11. Distribution of a public safety crime update to tenants and landlords within the SRA. | Manager | Weekly | 1st July 2017 – 30th June 2018 | Obtain public safety statistics from SA Police and Security Service provider within the SRA area and distribute weekly. |  |
| 12. Regular interaction/blitz operations with SAPS, Traffic, Law Enforcement, etc. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Quarterly report back to Board on outcome. |  |
| 13. Encourage companies to implement effective lighting at businesses. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Reporting to Board on improvements and requirements. |  |
| 14. Regulate efficient monitoring and maintenance of CCTV cameras. | Manager | Weekly | 1st July 2017 – 30th June 2018 | Weekly assessment and evaluation of service by Manager and report back to Board. |  |
| 15. Expansion of CCTV cameras. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Tabling of report to Board for evaluation and subsequent implementation. |  |

| PROGRAM 3 - CLEANSING INITIATIVES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Identify and address the root causes of litter and illegal dumping. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Quarterly evaluation of the number/type of root causes and the environmental design contributing to grime. Report to Board. |  |
| 2. Address root causes of grime. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Number of contributing factors addressed. Report to Board. |  |
| 3. Co-ordinate a cleansing service. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Report to Board about meetings with cleaners, surveys of area, keep statistics pertaining to number of bins filled with litter that are removed. |  |
| 4. Co-ordinate the provision and emptying of litter bins with the City of Cape Town. | Manager | Monthly | 1st July 2017 – 30th June 2018 | Monthly evaluations and inspections with reports to COCT. |  |
| 5. Co-ordination of signage warning offenders with regard to illegal dumping and littering, and monitoring the presence of illegal posters/signage. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Evaluate, investigate and implement. Report illegal posters/signage to COCT and report to Board. |  |
| 6. Encourage maintenance of buildings and landscaping of street frontages. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Encouraging owners/tenants to maintain buildings/street frontages by means of newsletters, competitions. |  |
| 7. Appointment of service provider. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Contract/competitive process every 2 years. |  |
| Program 4 - URBAN MANAGEMENT INITIATIVES |  |  |  |  |  |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Awareness campaigns relating to environmental issues. Promote education on waste/water pollution and safe waste disposal methods. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Newsletters, functions, education of employers and employees. |  |
| 2. Promote a working relationship with the authorities of the City of Cape Town as a “top up” municipal service to address: * Street lighting; * Dumping/refuse removal; * Missing drain covers/cleaning of drains; * Planting, felling, trimming, pruning of trees; * Maintenance of road surfaces, sidewalks; * Cutting of grass/removal of weeds * Cleansing, placing and emptying of litter bins; * Road markings/traffic signs. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Assessment and evaluation of the SRA area and reports received from the SRA’s security service provider, tenants and landlords. Analysis of shortcomings with reports to COCT. Quarterly report to SRA Board. |  |
| 3. Liaise with the relevant role players of the local authority. | Manager | Monthly | 1st July 2017 – 30th June 2018 | Monthly meetings with the relevant role players of the Local Authority regarding progress of identified shortcomings. |  |
| 4. Compile a priority list of essential needs to enhance the objectives of the SRA. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Submission to SRA Board regarding services/financial approval. |  |
| 5. Circulate useful COCT contact numbers to Members. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Circulate and update information by means of newsletters. |  |
| 6. Landscaping /Environmental greening projects to uplift the SRA area. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Assessment, quotations for submission to SRA Board. |  |

| Program 5 - SOCIAL INTERVENTION INITIATIVES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Recycling project where funds generated are directed to assist and uplift a neighboring school. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Report to Board. |  |
| 2. Addressing the presence of abandoned and neglected children. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Report to SA Police Service Bellville for the necessary action involving the Magistrates Court and welfare organizations. |  |
| 3. Addressing the presence of street people. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Report to an assessment centre in Bellville for the necessary support. |  |
| 4. Addressing animal cruelty and abandoned animals. (strays and working cart horses) | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Meetings with Animal anti-cruelty, Cart-horse Association. Report to SRA Board. |  |
| 5. Link social development programs and initiatives with those of the COCT – Social Development Department Program. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Program put in place with local social development department for upliftment. |  |

| Program 6 - MARKETING INITIATIVES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | DURATION | PERFORMANCE INDICATOR | COMMENTS |
| 1. Distribution of newsletters pertaining to activities occurring in the SRA area. | Manager | Quarterly | 1st July 2017 – 30th June 2018 | Newsletter, flyers etc. |  |
| 2. Appropriate signage within the industrial area promoting the SRA. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Investigate, evaluate, quotations for submission to CID Board. |  |
| 3. Media coverage of:- Promoting the SRA and business prospects of the area. | Manager | Quarterly | 1st July 2017– 30th June 2018 | Quarterly assessment and evaluation of media coverage. |  |
| 4. Maintaining of a website for the SRA. | Manager | Ongoing | 1st July 2017 – 30th June 2018 | Regular updating of website. |  |