| TRIANGLE INDUSTRIAL CITY IMPROVEMENT DISTRICT NPC (CID) ANNUAL IMPLEMENTATION PLAN 1st July 2018 to 30th June 2019 |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROGRAM 1 – MANAGEMENT & OPERATIONS |  |  |  |  |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Effective Management of the CID by a Board of Directors elected by its Members and operated by a management team that is appointed by the Board of Directors. | Directors Manager | Ongoing | Quarterly feedback at Board meetings. | Effective Management will be aimed at facilitating investment in the area with promotion of economic growth and sustainable development coupled with new job creation activities. These would relate to environmental issues, effective communication with property / business owners, and promotion of membership to the CID, etc. |
| - Operational CID office. | Directors Manager | Ongoing | Appointment of staff and provision of functional CID office open to all property owners. |  |
| - Board Meetings. | Manager | Ongoing | Quarterly Board meetings with reports tabled by different portfolio chairs. |  |
| - Financial report to CCT. | Director - Finance | Ongoing | Submit reports timeously by the 15th of the following month. |  |
| - Audited Financial Statements. | Finance Director | Annually | Unqualified Financial Audits submitted by 31 August to CCT. |  |
| - Communicating arrears list. | Manager | Ongoing | Table at Board meeting – observe and report concern over outstanding amount. Members in arrears cannot participate in meetings. |  |
| - AGM. | Manager | Annually | Host AGM and provide members with relevant information. |  |
| 2. Effective Management of Finances. | CID Board of Directors, Book keeper and Auditors. Director – Finance. | Ongoing | Preparation of budgets, regulation of expenditure, careful consideration of capital expenditure, regular inspection of financial status and financial registers. | The CID Board of Directors has numerous control mechanisms in place pertaining to approval of expenditure and record keeping. |
| 2.1. Mid-year review | Manager | Annually | Submit to CCT by end of January. |  |
| 3. Promote Membership to the CID, encouraging active participation in decision making processes. | Manager | Ongoing | Have a NPC membership that represents the CID community. Ensure that membership application requests are prominent on the web page. |  |
| 4. Facilitate effective communication with business owners and CID Members thus enabling the CID to provide an efficient service. | Manager | Ongoing | Newsletters, meetings, reports to CID Board. |  |
| 5. Continued updating of CID Data Base in order to promote effective communication with property/ business owners on their integration into the CID area. | Manager | Ongoing | Visits to newcomers. Promotion of CID’s activities in newsletter. |  |
| 5.1. Submit Management Report and Annual Financial Statements to Sub-Council. | Manager | Annually | Within 3 months of AGM. |  |
| 5.2. Manage and monitor C3 notification process. | Manager | Monthly | Report number of C3 notification per month to the Board. |  |
| 5.3. Submit input to CCT IDP (Integrated Development Plan). | Manager | Annually | Annual submission to Sub Council. |  |
| 5.4. Submit input to CCT Capital and Operational Budget. | Manager | Annually | Annual submission to Sub Council. |  |
| 5.5. Review CID Budget. | Director - Finance | Annually | Submit review budget to CCT by 31 January. |  |
| 6. Comply with all Company Act requirements. | CID Board of Directors, Book keeper and Auditors. Director – Finance. | Annually | CIPC requirements: - Auditors – submit to CIPC within 10 business days of change. - Directors – Submit to CIPC within 10 business days of change. - Annual returns – submit to CIPC within 30 business days after the anniversary date of the NPC. - Membership – maintain membership. |  |
| 7. Obtain Annual Tax clearance certificate. | Book keeper | Annually | Within one month after expiry date of current TCC. |  |
| 8. Compile annual CID Implementation Plan and Budget. | Manager | Annually | The Board submit draft Implementation Plan and Budget to CID unit for verification and tabling at AGM. |  |
| 9. Do VAT reconciliation and tax returns. | Book keeper | Bi monthly and annually |  |  |

| PROGRAM 2 – SECURITY / LAW ENFORCEMENT INITIATIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Review of current public safety plan. | Manager | Ongoing | Incorporate findings in Public Safety Plan and Board approval. |  |
| 2. Keep record of public safety statistics/ incidents and identify “hot spot” areas. | Manager Security Service Provider | Monthly | Measurement. Comparisons. Monthly submission to Board. |  |
| 3. Identify the root causes of public safety by conducting the necessary research/analysis. | Manager | Quarterly | Quarterly evaluation of the number/type of root causes identified and amend operational plan. |  |
| 4. Identify environmental design contributing to public safety. | Manager | Quarterly | Quarterly evaluation of environmental design contributing to public safety and amend operational plan. |  |
| 5. Address root causes of crime in conjunction with the SAPS, Local Authority, Security Service and other stake holders. | Manager | Ongoing | Number of contributing factors addressed through stakeholders reported to Board monthly. |  |
| 6. Liaise with the South African Police Service with regard to the effective policing of the CID area. | Manager | Monthly | Monthly meetings with the relevant role players within SAPS and give feedback to service provider and Board. |  |
| 7. Identify shortcomings of the SAPS in relation to the effective policing of the CID area. | Manager | Quarterly | Quarterly evaluation of shortcomings and amend operational plan accordingly. |  |
| 8. Regular interaction/blitz operations with SAPS, Traffic, Law Enforcement, etc. | Manager | Quarterly | Quarterly report back to Board on outcome. |  |
| 9. Co-operate with the SA Police Service. Active participation by CID and assistance to Police by gathering relevant information to facilitate the development and implementation of both effective and practical crime prevention strategies for the CID area. | Manager | Monthly | Monthly meetings with the SA Police Service with monthly report to the CID Board. |  |
| 10. On-site inspection of security patrol officer. | Manager | Ongoing | Report findings to Board with recommendations where applicable. |  |
| 11. Provide an efficient Public Safety Service. | Manager | Ongoing | Appointment of Public Safety service provider by means of a competitive process (2-year contract) and deployment of officers accordingly. |  |
| 12. Distribution of a public safety crime update to tenants and landlords within the CID. | Manager | Weekly | Obtain public safety statistics from SA Police and Security Service provider within the CID area and distribute weekly. |  |
| 13. Encourage companies to implement effective lighting at businesses. | Manager | Quarterly | Reporting to Board on improvements and requirements. |  |
| 14. Regulate efficient monitoring and maintenance of CCTV cameras. | Manager | Weekly | Weekly assessment and evaluation of service by Manager and report back to Board. |  |
| 15. Extension of current CCTV cameras. | Manager | Ongoing | Tabling of report to Board for evaluation and subsequent implementation. |  |
| 16. Refurbish the existing fence in Uranium Street. | Manager | Ongoing | Obtain quotations for implementation and submit to the Board. |  |
| 17. Upgrading of wall on public open space/Reactor Street. | Manager | Ongoing | Obtain quotations for implementation and submit to the Board. |  |
| PROGRAM 3 - CLEANSING INITIATIVES |  |  |  |  |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Identify and address the root causes of litter and illegal dumping. | Manager | Quarterly | Quarterly evaluation of the number/type of root causes and the environmental design contributing to grime. Report to Board. |  |
| 2. Address root causes of grime. | Manager | Ongoing | Number of contributing factors addressed. Report to Board. |  |
| 3. Co-ordinate a cleansing service. | Manager | Ongoing | Report to Board about meetings with cleaners, surveys of area, keep statistics pertaining to number of bins filled with litter that are removed. |  |
| 4. Co-ordinate the provision and emptying of litter bins with the City of Cape Town. | Manager | Monthly | Monthly evaluations and inspections with reports to COCT. |  |
| 5. Co-ordination of signage warning offenders with regard to illegal dumping and littering, and monitoring the presence of illegal posters/signage. | Manager | Ongoing | Evaluate, investigate and implement. Report illegal posters/signage to CCT and report to Board. |  |
| 6. Encourage maintenance of buildings and landscaping of street frontages. | Manager | Quarterly | Encouraging owners/tenants to maintain buildings/street frontages by means of newsletters, competitions. |  |
| Program 4 - URBAN MANAGEMENT INITIATIVES |  |  |  |  |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Awareness campaigns relating to environmental issues. Promote education on waste/water pollution and safe waste disposal methods. | Manager | Ongoing | Newsletters, functions, education of employers and employees. |  |
| 2. Promote a working relationship with the authorities of the City of Cape Town as a “top up” municipal service to address: * Street lighting; * Dumping/refuse removal; * Missing drain covers/cleaning of drains; * Planting, felling, trimming, pruning of trees; * Maintenance of road surfaces, sidewalks; * Cutting of grass/removal of weeds * Cleansing, placing and emptying of litter bins; * Road markings/traffic signs. | Manager | Ongoing | Assessment and evaluation of the CID area and reports received from the CID’s security service provider, tenants and landlords. Analysis of shortcomings with reports to CCT. Quarterly report to SRA Board. |  |
| 3. Liaise with the relevant role players of the local authority. | Manager | Monthly | Monthly meetings with the relevant role players of the Local Authority regarding progress of identified shortcomings. |  |
| 4. Compile a priority list of essential needs to enhance the objectives of the CID. | Manager | Ongoing | Submission to CID Board regarding service/ financial approval. |  |
| 5. Circulate useful CCT contact numbers to Members. | Manager | Quarterly | Circulate and update information by means of newsletters. |  |
| 6. Landscaping /Environmental greening projects to uplift the CID area. | Manager | Ongoing | Assessment, quotations for submission to CID Board. |  |

| Program 5 - SOCIAL INTERVENTION INITIATIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Recycling project where funds generated are directed to assist and uplift a neighboring school. | Manager | Ongoing | Report to Board. |  |
| 2. Addressing the presence of abandoned and neglected children. | Manager | Ongoing | Report to SA Police Service Bellville for the necessary action involving the Magistrates Court and welfare organizations. |  |
| 3. Addressing the presence of street people. | Manager | Ongoing | Report to an assessment centre in Bellville for the necessary support. |  |
| 4. Addressing animal cruelty and abandoned animals. (strays and working cart horses) | Manager | Ongoing | Meetings with Animal anti-cruelty, Cart-horse Association. Report to CID Board. |  |
| 5. Link social development programs and initiatives with those of the CCT – Social Development Department Program. | Manager | Ongoing | Program put in place with local social development department for upliftment. |  |

| Program 6 - MARKETING INITIATIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTION STEPS | RESPONSIBLE | FREQUENCY per year | PERFORMANCE INDICATOR | COMMENTS |
| 1. Distribution of newsletters pertaining to activities occurring in the CID area. | Manager | Quarterly | Newsletter, flyers etc. |  |
| 2. Appropriate signage within the industrial area promoting the CID. | Manager | Ongoing | Investigate, evaluate, quotations for submission to CID Board. |  |
| 3. Media coverage of:- Promoting the CID and business prospects of the area. | Manager | Quarterly | Quarterly assessment and evaluation of media coverage. |  |
| 4. Maintaining of a website for the CID. | Manager | Ongoing | Regular updating of website. |  |