TRIANGLE INDUSTRIAL CITY IMPROVEMENT DISTRICT NPC (TICID) 5 YEAR IMPLEMENTATION PLAN 1st JULY 2021 – 30th JULY 2026 CITY IMPROVEMENT DISTRICT

| MANAGEMENT & OPERATIONS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Effective Management of the TICID | Functional Board meetings to ensure the TICID Business plan is implemented. | Ongoing |  |  |  |  |  | Manager / Board |  |
| 2. Operational TICID office | Appointment of staff and provision of functional TICID office open to all property owners. | Ongoing |  |  |  |  |  | Manager / Board |  |
| 3. Board meetings | Bi-monthly Board meetings. | 6 | 6 | 6 | 6 | 6 | 6 | Manager / Board | Quorum of director’s present at every meeting, keep minutes and file resolutions. |
| 4. Monthly Progressive Income and Expenditure Report to CCT | Submit reports to the CID Department timeously. | 12 | 12 | 12 | 12 | 12 | 12 | TICID Accountant | Submit reports to the CID Department by the 15th of the following month. |
| 5. Audited Financial Statements | Audited Annual Financial Statements with an unqualified finding. | 1 | 1 | 1 | 1 | 1 | 1 | Finance Director | Submitted to the City by 31 August each year. |
| 6. Communicating arrears list | Board Members in arrears cannot participate in meetings. | 12 | 12 | 12 | 12 | 12 | 12 | Manager | Observe and report concern over outstanding amount. Members in arrears cannot participate in meetings. |
| 7. Annual General Meeting | Annual feedback to members at AGM and complying with legal requirements. | 1 | 1 | 1 | 1 | 1 | 1 | Manager | Host successful AGM before the 31 December. |
| 8. Effective Management of Finances | Preparation of budgets, regulation of expenditure, careful consideration of capital expenditure, regular inspections of financial status and financial registers. | Ongoing |  |  |  |  |  | Board, Bookkeeper and Auditors. Director – Finance. | The CID Board of Directors has numerous control mechanisms in place pertaining to approval of expenditure and record keeping. |
| 9. Mid-year performance review | Board approved mid-year review submitted to the CCT by end of February. | Annually | 1 | 1 | 1 | 1 | 1 | Manager / Board | Submit Board minutes and approved Mid-year performance review to the CCT by end of February. Ensure under / non-performance areas are addressed before the end of the financial year. |
| 10. Promote Membership to the TICID, encouraging active participation in decision making processes | Have an NPC membership that represents the TICID community. Ensure that the CID membership list are prominent on the website and kept up to date. | Ongoing |  |  |  |  |  | Manager |  |
| 11. Facilitate effective communication with business owners and TICID members thus enabling the TICID to provide an efficient service | Newsletters, meetings, reports to CID Board. | Ongoing |  |  |  |  |  | Manager | Keep property owners informed. |
| 12. Appointment of relevant service providers | Appointment of appropriately qualified service providers. | 2 Years | 2Y |  | 2Y |  | 2Y | Manager / Board | Service providers to be reappointed or new providers to be appointed in last year of contract period by means of a competitive process. |
| 13. Continued updating of TICID Data base to promote effective communication with property/business owners on their integration into the TICID area | Visit to newcomers. Promotion of CID’s activities in newsletter. | Ongoing |  |  |  |  |  | Manager |  |
| 14. Submit Management Report and Annual Audited Financial Statements to Sub-Council | Submit AFS and annual report to Sub Council within 3 months of AGM. | Annually | 1 | 1 | 1 | 1 | 1 | Manager | Submit proof of submission to CID Department. |
| 15. Submit input to CCT IDP (Integrated Development Plan) | Annual submissions to Sub Council Manager | Annually | 1 | 1 | 1 | 1 | 1 | Manager | October to February of every year. |
| 16. Submit input to CCT Capital and Operational Budget | Annual submission to Sub council. | Annually | 1 | 1 | 1 | 1 | 1 | Manager | By September of each year. |
| 17. Review CID Budget | Board approved budget review to the CCT by end of February. | Annually | 1 | 1 | 1 | 1 | 1 | Manager | Submit Board minutes and approved adjustment budget to the CCT by end of February. |
| 18. Comply with all Company Act requirements | CIPC compliance. | Annually | 1 | 1 | 1 | 1 | 1 | Company secretary and Director – Finance. | CIPC requirements: Auditors / Directors – submit to CIPC within 10 business days of change. Annual returns – submit to CIPC within 30 business days after the anniversary date of the NPC. |
| 19. Obtain Annual Tax Clearance Certificate | Within one month after expiry date. | Annually | 1 | 1 | 1 | 1 | 1 | Bookkeeper | Submit PIN to CCT Supply Chain Management Department. |
| 20. Compile annual approval of Implementation Plan and Budget | Submit draft Implementation Plan and Budget to CID Department for verification and tabling at AGM. Obtain approval from Members at AGM. | Annually | 1 | 1 | 1 | 1 | 1 | Manager / Bookkeeper |  |
| 21. Do VAT reconciliation and tax returns | Bi-monthly VAT returns and annual tax returns submitted to SARS on time. | Bi-monthly | 6 | 6 | 6 | 6 | 6 | Bookkeeper |  |
| 22. Directors to receive relevant documentation | At the first meeting after the AGM, supply all Directors with relevant CID documents. | Annually | 1 | 1 | 1 | 1 | 1 | Manager |  |
| 23. Allocation of portfolios | At first Board meeting after AGM elect chairperson and assign portfolios to the directors. | Annually | 1 | 1 | 1 | 1 | 1 | Manager / Board |  |
| 24. Declaration of Interest | Ensure all directors and manager sign DOI at Board meetings. | Bi-monthly | 6 | 6 | 6 | 6 | 6 | Manager |  |

| PUBLIC SAFETY |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Review of current public safety plan | Incorporate findings in Public Safety Plan and Board approval. | Ongoing |  |  |  |  |  | Manager |  |
| 2. Keep record of public safety statistics/incidents and identify hot spot areas | Measurement. Comparisons and submission to Board. | Monthly | 12 | 12 | 12 | 12 | 12 | Manager |  |
| 3. Identify the root causes of public safety by conducting the necessary research/analysis | Evaluation of the number/type of root causes identified and amend operational plan. | Ongoing |  |  |  |  |  | Manager |  |
| 4. Identify environmental design contributing to public safety | Evaluation of environmental design contributing to public safety and amend operational plan. | Ongoing |  |  |  |  |  | Manager |  |
| 5. Address root causes of crime in conjunction with SAPS, Local Authority, Security Service, and other stakeholders | Number of contributing factors addressed through stakeholders reported to Board. | Ongoing |  |  |  |  |  | Manager / Public Safety Service provider |  |
| 6. Liaise with the South African Police Service regarding the effective policing of the TICID area | Monthly meetings with the relevant role players within SAPS and give feedback to service provider. | Monthly | 12 | 12 | 12 | 12 | 12 | Manager |  |
| 7. Identify shortcomings of SAPS in relation to the effective policing of the TICID area | Quarterly evaluation of shortcomings and amend operational plan accordingly. | Quarterly | 4 | 4 | 4 | 4 | 4 | Manager |  |
| 8. Regular interaction/blitz operations with SAPS, Traffic, Law Enforcement, etc. | Quarterly report back to Board | Quarterly | 4 | 4 | 4 | 4 | 4 | Manager |  |
| 9. Co-operate with the SA Police Service. Active participation by TICID and assistance to Police by gathering relevant information to facilitate the development and implementation of both effective and practical crime prevention strategies for the TICID area | Monthly meetings with the SA Police Service and report to the CID Board. | Monthly | 12 | 12 | 12 | 12 | 12 | Manager |  |
| 10. On-site inspections of security patrol officers | Report finding to the Board with recommendations where applicable. | Ongoing |  |  |  |  |  | Manager |  |
| 11. Appointment of Service provider | Appointment of Public Safety service by means of a competitive process and deployment of officers accordingly. | Ongoing |  |  |  |  |  | Manager / Board |  |
| 12. Provide an efficient Public Safety service | Deployment of officers accordingly. | Ongoing |  |  |  |  |  | Manager |  |
| 12. Maintain a manned centrally located office open to the members of the TICID to request Public Safety assistance or report information | Appropriately manned and equipped office. | Ongoing |  |  |  |  |  | Manager |  |
| 13. Distribution of public safety crime update to tenants and landlords within the TICID | Obtain public safety statistics from SA Police and Security Service provider within the TICID area and distribute weekly. | Ongoing |  |  |  |  |  | Manager |  |
| 14. Encourage companies to implement effective lighting at businesses | Newsletters, crime updates and reporting to Board. | Ongoing |  |  |  |  |  | Manager |  |
| 15. Regulate efficient monitoring and maintenance of CCTV cameras | Assessment and evaluation of service and report to Board. | Ongoing |  |  |  |  |  | Manager |  |

| MAINTENANCE AND CLEANSING |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Identify and address the root causes of litter and illegal dumping | Evaluation of the number/type of root causes and the environmental design contributing to grime. Report to Board. | Quarterly | 4 | 4 | 4 | 4 | 4 | Manager |  |
| 2. Co-ordinate a cleansing service | Report to Board about meetings with cleaners, surveys of area, keep statistics pertaining to number of bins filled with litter that are removed. | Ongoing |  |  |  |  |  | Manager |  |
| 3. Co-ordinate the provision and emptying of litter bins with the City of Cape Town | Monthly evaluations and inspections with reports to CCT. | Monthly | 12 | 12 | 12 | 12 | 12 | Manager |  |
| 4. Co-ordination of signage warning offenders with regard to illegal dumping and littering, and monitoring the presence of illegal posters/signage | Evaluate, investigate, and implement. Report illegal posters/signage to CCT and report to Board. | Ongoing |  |  |  |  |  | Manager |  |
| 5. Encourage maintenance of buildings and landscaping of street frontages | Encouraging owners/tenants to maintain buildings/street frontages by means of newsletters, competitions. | Ongoing |  |  |  |  |  | Manager |  |
| 6. Appointed Cleansing service provider | Appointment of appropriately qualified service provider. | 2 Years | 1Y |  | 1Y |  | 1Y | Manager / Board | Service providers to be reappointed or new providers to be appointed in last year of contract period by means of a competitive process. |

| ENVIRONMENTAL DEVELOPMENT/URBAN MANAGEMENT INITIATIVES |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Awareness campaigns relating to environmental issues. Promote education on waste/water pollution and safe waste disposal methods | Newsletters, functions. | Ongoing |  |  |  |  |  | Manager |  |
| 2. Promote a working relationship with the authorities of the City of Cape Town as a “top up” municipal service to address: * Street lighting / Lamp poles * Dumping/refuse removal * Missing/damaged drain covers * Planting, felling, pruning of trees * Maintenance of road surfaces and sidewalks * Placing and emptying of litter bins * Blocked and damaged drains * Road markings/traffic signs | Assessment and evaluation of the TICID area. Analysis of shortcomings with reports to the CCT. | Ongoing |  |  |  |  |  | Manager |  |
| 3. Liaise with the relevant role players of the local authority | Meetings with the relevant role players of the Local Authority regarding progress of identified shortcomings. | Ongoing |  |  |  |  |  | Manager |  |
| 4. Compile a priority list of essential needs to enhance the objectives of the CID | Submission to CID Board regarding service/financial approval. | Ongoing |  |  |  |  |  | Manager |  |
| 5. Circulate useful CCT numbers to Members | Circulate and update information by means of newsletters. | Annually or as required | 1Y | 1Y | 1Y | 1Y | 1Y | Manager |  |
| 6. Environmental greening/upgrading projects to uplift the TICID area | Assessment, quotations for submission to Board. | Ongoing |  |  |  |  |  | Manager |  |

| SOCIAL INTERVENTION INITIATIVES |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Recycling project where funds generated are directed to assist a neighboring school | Report to Board. | Ongoing |  |  |  |  |  | Manager |  |
| 2. Addressing the presence of abandoned and neglected children | Report to SA Police Service Bellville for the necessary action involving the Magistrates Court and welfare organizations. | Ongoing |  |  |  |  |  | Manager |  |
| 3. Addressing the presence of street people | Report to an Assessment Centre in Bellville for the necessary support. | Ongoing |  |  |  |  |  | Manager |  |
| 4. Addressing animal cruelty and abandoned animals | Meetings with Animal anti-cruelty, Cart horse association. Report to CID Board. | Ongoing |  |  |  |  |  | Manager |  |
| 5. Coordinate social development programs and initiatives with City Social Development Department | Keep minutes, reports quarterly | Quarterly | 4 | 4 | 4 | 4 | 4 | Manager |  |

| MARKETING INITIATIVES |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS |
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5 |  |  |
| 1. Distribution of Newsletters / Newsflashes pertaining to activities occurring in the TICID area | Informative newsletters distributed. | Monthly | 12 | 12 | 12 | 12 | 12 | Manager |  |
| 2. Appropriate signage within the industrial area promoting the TICID | Investigate, evaluate, quotations for submission to CID Board. | Ongoing |  |  |  |  |  | Manager | Signage to be visible and maintained. |
| 3. Media coverage of: - Promoting the TICID and business prospects of the area | Quarterly assessment and evaluation of media coverage. | Quarterly | 4 | 4 | 4 | 4 | 4 | Manager |  |
| 4. Maintaining of a website for the TICID | Regular updating and informative website in compliance with CID legislation. | Ongoing |  |  |  |  |  | Manager |  |